## Sprint Backlog
As a user, I want to submit an article to the System to get a veracity score.
As a Business Owner, I want the Developer Team Email content captured.
As a developer, I want to define "Submit" so that I can understand system inputs formats and structures
As Developer Team, we need to understand how veracity will be represented, (relative, absolute …) so that we can define rational user outputs that we can provide as the results of the article analysis.
As Developer Team, we need to determine whether veracity "score" will be represented by a reliability score that determines the likely hood that the vacity score is accurate.

## Sprint 1 Problem Definition
Assigned To | Story | Engineering Tasks | Acceptance Criteria | Task Complete | Story Complete
Brett | As a developer, I want to define the Source and Structure of the system input (article).
No
Andy and Lew | As the developer team, we want to define veracity, so that we can assign the veracity score to an article.
No
Bruce | As Project Owner, I want a Presentation Outline that can be used for all presentations to include the Final Presentation
Create basic outline for entire project development Sprint Process
No
Create presntation Slides needed for Sprint 1
No
While the Presentation Outline is a living document, that changes throughout the project, it is defined as done at the end of each Sprint when the developer team consensus determines that it is done.
No
Jacques | As Business Owner, I want a Project Terms Lexicon.
Coordinate with the story team that "I want understand risks to successful veracity score system development", to use their definition as the one for risks in the lexicon
No
Coordinate with the story team that "we want to define veracity", to use their definition as the one for veracity in the lexicon
No
Coordinate with the story team that "I want to know the Project Assumptions (what is input?, veracity components and reliability)", to use their definition as the one for Project Assumptions in the lexicon
No
Determine Data term meaning for the lexicon
No
Determine Collection term meaning for the lexicon
No
Compile other terms' list and their meanings for the lexicon
No
Lew | As Project Owner, I want understand risks to successful veracity score system development
No
Jacques | As Business Owner, I want to know the Project Assumptions (what is input?, veracity components and reliability)
Determine article language that will be modeled and analyzed (English)
No
Determine article reiability score will be modeled and analyzed
No
Determine whether article fraud detection will be modeled and analyzed
No
Determine whether Journal in Blackboard or GitHub mechanisms will be used for managing tasks/stories.
No
Determine other Project Assumptions and write them down
No
Bruce | As Developer Team, we want to determine candidate analytic methods that can be associated with potential veracity features
No
Bruce | As Developer Team, we want to determine what analytic problem type this project is (i.e. classification, anomaly detection, or multiple types and which ones, ...)
No